BTS-SYNTHETIC  |  ENTERPRISE DATA PLATFORM

Proposal Response

Acme Corp — Enterprise Data Platform RFP

| Prepared for | Acme Corp — Procurement & CDO Office |
| --- | --- |
| Procurement lead | Sarah Chen, VP Procurement |
| Technical lead | Marcus Webb, Chief Data Officer |
| Submitted by | BTS-Synthetic, Deal Desk |
| Response date | 2026-05-26 (RFP deadline) |

CONFIDENTIAL — prepared in response to Acme Corp RFP, 2026-05-12. Contains commercial terms subject to negotiation.

1. Executive Summary

BTS-Synthetic is the right partner for Acme Corp's replacement of Teradata and ad-hoc cloud analytics with a single, governed, multi-region lakehouse on Azure. We meet every functional requirement in your RFP, with our strongest BI integration — Power BI DirectQuery — purpose-built for the exact pattern your 600 analysts use today.

Why BTS-Synthetic — three reasons

Functional fit (30%):  Production-hardened Power BI DirectQuery adapter plus per-table EU residency on customer-owned Azure Blob. Microsoft Fabric forces data into OneLake; Snowflake bolts streaming on the side; Databricks pushes the optimisation work onto your team. We ship the architecture you actually asked for.

Total cost of ownership (20%):  5-year fixed pricing with transparent CPI+2% escalator (capped at 5%). 23% off list opening, $693K Year 1 net. Comparable customer (Initech Sensors, industrial IoT) realised 18% lower 3-year TCO than the Microsoft Fabric "free with E5" alternative once governance and real-time tooling were properly costed.

Implementation timeline (15%):  18-month runway to your 2027 Teradata decommission gate, with first production workload live in 8 weeks. Phased migration, dual-run validation, and a 90-day buffer before your hard deadline.

Commercial headline

$693,000 Year 1 net (23% off $900K list), with 3-year committed term at flat 23% discount and CPI+2% escalators in Years 2–3. Optional 99.99% Premium Availability tier available as a separately priced line item at $100K/year for active-active EU + US East deployment. 5-year total net: $3.65M (excluding the 99.99% premium). Net 60 payment terms; PoC fees credited 100% to Year 1.

Conditions of bid — four contractual blockers

We will not silently accept four positions in your draft that, as written, prevent us from underwriting the contract. We propose workable counter-positions on each and request a pre-submission redline call with Acme Counsel before 2026-05-26.

§4.1 Uncapped breach liability —  We propose a cap at 24 months of fees paid (~$1.8M), with mutual carve-outs for gross negligence and IP infringement. Our cyber liability insurance is voided by uncapped exposure.

§4.3 SLA termination on any miss —  Acme may immediately terminate plus full-month refund on any single SLA miss. We propose 99.95% with service-credit remedy, termination only after three failures in any rolling 12-month period with cure rights. The 99.99% target is available as a Premium Availability tier (priced).

§4.4 Full IP assignment of all work product —  We propose perpetual royalty-free licence-back of customer-specific configurations and integrations. Platform IP must remain with BTS-Synthetic. Precedent: Stark Industries (2026-02) accepted this exact structure.

§4.2 No-notice, four-per-year vendor-funded audit —  We propose one audit per calendar year with 30 days' notice, plus an SOC 2 Type II report on demand. Four unannounced audits are operationally and contractually incompatible with our subprocessors.

Key risk

Microsoft Fabric will position itself as "free with E5." Our experience at Initech Sensors (industrial IoT, won 2025-11) shows that Fabric's real-time governance and per-table residency are 12–18 months behind ours, and the true cost emerges in Professional Services and real-time tooling. We invite Acme to test this in a head-to-head TCO model — we will provide ours in writing.

2. Our Understanding of Acme's Need

Acme Corp operates a global industrial IoT and manufacturing footprint generating large-volume sensor telemetry from 40,000 devices and ~30 internal systems. The current Teradata + ad-hoc cloud-analytics estate is being retired by end of 2027. The replacement must be:

Azure-native, with first-class Power BI for the existing 600-analyst base.

Lakehouse-architected, on open file formats (Parquet, Delta, Iceberg), to avoid future portability lock-in.

Multi-region, with EU customer data pinned to EU regions for GDPR compliance.

Capable of handling 80,000 events per second peak ingest while supporting analyst self-service, batch ETL from 30+ sources, and a forthcoming predictive maintenance ML programme.

Commercially predictable across a 5-year horizon (3-year initial + 2-year renewal), with transparent pricing and no surprise escalators.

We read Acme's evaluation criteria — 30% functional fit, 25% commercial, 20% TCO, 15% implementation, 10% stability/references — as a clear signal that the platform decision will be made on capability and total economic outcome, not on opening discount alone. Our response is structured accordingly.

3. Technical Proposal

3.1 Capability map against Acme's requirements

| Acme Requirement | Fit | Evidence |
| --- | --- | --- |
| Real-time ingest — 40K IoT devices / 80K events/sec peak | FULL FIT | Native Kafka and Kinesis streaming tested to 250K events/sec. 3× headroom on Acme's peak. |
| Batch ETL from 30+ internal sources | FULL FIT | 80+ certified batch connectors plus Debezium-compatible CDC covers all standard enterprise sources. |
| BI/reporting for 600 analysts — Power BI mandatory | FULL FIT | Dedicated Power BI DirectQuery adapter — our most mature BI integration. |
| Self-service data prep for 150 data engineers | FULL FIT | Low-code self-service prep UI plus SQL, notebooks (Python/R/Scala), and streaming compute. |
| Machine learning pipelines (predictive maintenance, planned) | FULL FIT | Model registry, feature store (offline + online), native serving with autoscaling, bring-your-own-model support. |
| Scale: 280 TB now, 12 TB/month growth (~424 TB by EOY 2027) | FULL FIT | BYO Azure Blob object storage; petabyte-scale lakehouse. No architectural ceiling at Acme's projected growth. |
| Multi-region: primary EU, secondary US East | FULL FIT | Multi-cloud, multi-region within each cloud. Active-active configuration supported. |
| EU data residency for EU customer data | FULL FIT | Per-table residency pinning, GDPR-aligned DPA available, row/column-level security, PII masking, audit logs to customer SIEM. |
| Lakehouse architecture preferred | FULL FIT | Native lakehouse — core product architecture, not retrofit. |
| Open file formats: Parquet, Delta, Iceberg | FULL FIT | All three natively supported. Customer retains data ownership and portability. |
| Microsoft / Azure primary cloud | FULL FIT | Azure Blob BYO storage; Power BI DirectQuery; Azure-native deployment pattern. |
| Teradata decommission through 2027 | PARTIAL FIT | 16-week Teradata-class benchmark fits the timeline; 30+ sources adds complexity. We propose a phased migration plan (see §4) with a 90-day buffer before your hard deadline. |
| 99.99% monthly uptime | PARTIAL FIT | Standard SLA is 99.95%. 99.99% Premium Availability tier offered as a priced line item — designed for the EU + US East active-active topology Acme already requires. |

Overall fit: HIGH. No outright capability gaps. Two partial fits are both addressable: the SLA via our Premium Availability tier, and the migration via a phased plan documented in §4.

3.2 Where we lead — three technical differentiators

1. Power BI DirectQuery — mature, not bolted on

Acme's 600 analysts use Power BI today. Our DirectQuery adapter is production-hardened and is our single most invested BI integration. Competitors require workarounds (Snowflake), premium SKUs (Fabric, where OneLake lock-in is a side effect), or significant customer-side engineering (Databricks). This is the lowest-friction path for your existing analyst base.

2. Per-table EU residency on open formats, customer-owned storage

We deliver per-table residency pinning on customer-owned Azure Blob, with data stored in Parquet, Delta, or Iceberg. Fabric stores data inside OneLake; Databricks multi-region residency requires significant custom configuration. With BTS-Synthetic, Acme retains data ownership, data portability, and regulatory defensibility for EU customer data in the same architecture.

3. Streaming and batch on a single lakehouse engine

Acme's estate spans 80K events/second IoT ingest and 30+ batch ETL sources. We run both natively on the same lakehouse — same governance, same catalog, same security model. Snowflake requires Snowpipe plus separate streaming tooling; Microsoft Fabric's real-time layer is materially less mature. The operational and licensing simplification is real and quantifiable.

3.3 Honest disclosures — risks and how we will mitigate

| Risk / weakness | Our mitigation |
| --- | --- |
| 99.99% SLA is a premium add-on, not standard | Disclosed up-front in §5 commercial proposal as a priced line item ($100K/year). Premium Availability requires active-active multi-region, which Acme already requires for EU + US East. The architecture is not extra — only the contractual commitment is. |
| 30+ source migration complexity | We do not commit to a hard cutover date in M0. Phased plan in §4 includes a dedicated discovery sprint (Weeks 1–4) before locking the migration schedule. M7 gate at 2027-10-01 builds a 90-day buffer to your end-2027 hard deadline. |
| Sub-100ms streaming latency — unconfirmed scope | Our streaming latency is ~250 ms – 1 s end-to-end. Acme's RFP does not specify a latency SLO, but the predictive maintenance use case can imply one. We have included this as a clarification question in §11. We will not over-commit before a written answer. |

4. Implementation Plan

Assumed contract signature: 2026-07-01. Teradata decommission deadline: 2027-12-31. 18-month runway, against our 24-week benchmark for very large multi-region, multi-source migrations. Plan absorbs scope risk via a M7 read-only gate at 2027-10-01, leaving a 90-day buffer before Acme's hard cutover.

| # | Milestone | Target | Outcome |
| --- | --- | --- | --- |
| M0 | Kickoff & Discovery | Weeks 1–4 — by 2026-07-29 | Source system inventory, EU residency config, Azure Blob provisioning, stakeholder alignment, locked migration schedule. |
| M1 | Foundation: Streaming + Core Lakehouse | Weeks 5–12 — by 2026-09-23 | IoT ingest pipeline live (Kafka → lakehouse); EU/US East active-active enabled; 99.99% Premium Availability activated. |
| M2 | First Production Workload | Week 8 — by 2026-08-26 | First Teradata workload migrated and dual-running; Power BI DirectQuery live for pilot analyst group. |
| M3 | Batch ETL Buildout | Weeks 13–24 — by 2026-12-23 | 30+ source connectors configured; CDC pipelines in production; data-quality validation against Teradata. |
| M4 | Full Teradata Parity | Weeks 17–32 — by 2027-02-17 | All Teradata workloads replicated and validated; dual-run period begins. |
| M5 | Analyst Rollout (600 users) | Weeks 25–36 — by 2027-04-01 | Power BI semantic layer finalised; self-service prep onboarded for 150 data engineers. |
| M6 | ML Pipeline Foundation | Weeks 33–44 — by 2027-06-01 | Feature store populated; model registry configured for predictive maintenance phase. |
| M7 | Teradata Decommission Gate | By 2027-10-01 | All workloads validated in production; Teradata switched to read-only; 90-day buffer to hard deadline. |
| M8 | Teradata Dark | By 2027-12-31 | Decommission complete on Acme's timeline; 3-month buffer absorbed by M7. |

Critical-path note: M0 source-system discovery is the schedule-defining sprint. We will not commit a final M3 batch ETL plan until M0 output is signed off by Acme's Chief Data Officer. This protects both parties against undiscovered legacy ETL debt.

5. Commercial Proposal — 5-Year Pricing

5.1 Headline

Year 1 ACV: $693,000 net (23% off $900,000 list). 3-year committed initial term at flat 23% discount with CPI+2% escalator (capped at 5%) in Years 2 and 3. 2-year renewal at standard band (20%) on a re-set list.

5.2 5-year pricing table — platform subscription

| Year | Period | List ACV | Discount | Escalator | Net ACV |
| --- | --- | --- | --- | --- | --- |
| Year 1 | 2026-07 → 2027-06 | $900,000 | 23% | — | $693,000 |
| Year 2 | 2027-07 → 2028-06 | $900,000 | 23% | CPI+2% (~3% est.) | $713,790 |
| Year 3 | 2028-07 → 2029-06 | $900,000 | 23% | CPI+2% (~3% est.) | $735,204 |
| Year 4 (renewal) | 2029-07 → 2030-06 | $926,100 | 20% | List reset at CPI | $740,880 |
| Year 5 (renewal) | 2030-07 → 2031-06 | $953,883 | 20% | CPI+2% (~3% est.) | $763,106 |
| 5-YEAR TOTAL |  |  |  |  | $3,645,980 |

5.3 Optional line item — 99.99% Premium Availability tier

| Add-on | Annual | 5-year |
| --- | --- | --- |
| 99.99% Premium Availability — active-active EU + US East | $100,000 / year | $500,000 over 5 years |

Includes the contractually committed 99.99% monthly uptime tier on the underlying service, with the architecture (active-active multi-region) already required by Acme's EU + US East topology. Quoted as a separately priced line item so Acme can elect this commercially.

5.4 Payment, prepay, and PoC credits

Payment terms — Net 60 on annual upfront billing.  Counter to RFP §3.2 (Net 90). Net 60 reflects the working-capital cost of longer terms on a $900K ACV ($15K–$25K/year) and is consistent with our Initech Sensors precedent.

Optional 3-year prepay incentive — additional 2% discount (25% total).  Multi-year prepay incentive available if Acme elects to prepay the full 3-year committed term at signature. Converts approximately $2.07M of net revenue upfront.

PoC credit —  Any PoC or pilot fees paid to BTS-Synthetic prior to signature are credited 100% against Year 1 ACV. Precedent: Wayne Manufacturing (2026-03).

Year 1 cash exposure —  Year 1 platform $693K + Premium SLA $100K + onboarding (one-off, separately scoped) = ~$793K cash to BTS-Synthetic in Year 1, before PoC credits.

5.5 Commercial walk-aways

In the interests of transparency: the floor we can hold without crossing into uncommercial territory is 27% off list. Discount demands beyond 27% would require either (a) a multi-year prepay, (b) reference-customer commitment, or (c) renegotiation of contractual blockers in §6. We do not bid against an undefined competitor floor; we bid on the value we deliver.

6. Contract Approach — Position by Position

Per the RFP's evaluation weighting on commercial flexibility (25%), we set out our position on every contentious clause in Acme's draft. Where we mark a clause BLOCKER, that clause is a hard condition of bid and we ask for a redline call with Acme Counsel before 2026-05-26.

| § | Clause | Verdict | Our position |
| --- | --- | --- | --- |
| §3.2 | Net 90 payment | COUNTER | Net 60 on annual upfront billing. Net 30 would be standard; we extend to Net 60 as a single payment-terms concession. |
| §3.3 | 35% minimum discount off list | COUNTER | Open at 23%, willing to negotiate to 25% on strategic terms; absolute floor 27% with multi-year prepay or reference commitment. |
| §3.4 | MFN for 5-year term | COUNTER | Reject 5-year MFN. Offer instead a contractual price-stability guarantee: list price for Acme's committed term will not rise beyond agreed CPI+2% escalator. Addresses the underlying concern (price shock) without the cross-book pricing rigidity of MFN. |
| §3.5 | Termination for convenience — 30 days, no ETF | COUNTER | Extend convenience-termination notice to 90 days. With annual upfront billing retained, Acme receives a pro-rated refund of unused prepaid term — not a full refund. |
| §4.1 | Uncapped liability for data breach | BLOCKER | Cap aggregate liability at 24 months of fees paid (~$1.8M), with mutual carve-outs for gross negligence and IP infringement. Uncapped exposure voids our cyber liability policy. Non-negotiable. |
| §4.2 | Audit — 4×/year, no notice, vendor-paid | BLOCKER | 1 audit per year with 30 days' prior notice; auditor under NDA. SOC 2 Type II report available on demand. Acme funds any audit beyond the first per year. 30-day notice requirement is non-negotiable (subprocessor contractual constraint). |
| §4.3 | 99.99% uptime; immediate termination on any miss | BLOCKER | 99.95% monthly uptime in standard MSA, with service-credit remedy. Termination right only after three SLA misses in any rolling 12-month period and after vendor cure period. 99.99% available as a priced Premium Availability tier (see §5.3) but not as the MSA default. |
| §4.4 | All work product IP vests in Acme | BLOCKER | Platform IP remains with BTS-Synthetic. Customer-specific configurations, integrations, and reports are licensed to Acme perpetually, royalty-free, with a right to use, modify, and create derivative works. Precedent: Stark Industries (2026-02). |
| §4.5 | Subprocessor prior consent at sole discretion | COUNTER | Maintain a public subprocessor list. 30-day advance notice before adding any subprocessor. Acme may object in writing within 15 days, triggering good-faith substitution or, as last resort, termination right with 90-day notice. AWS / Azure / GCP / Debezium / observability stack pre-approved at signing. |
| §2.3 | EU data residency | ACCEPT | Accepted as-is. Per-table residency pinning to EU regions; GDPR-aligned DPA executed at signature (Standard Contractual Clauses + Art. 28). Solutions engineering will confirm EU region coverage for Acme's specific data model. |

Bid/no-bid status

Legal review surfaces four (4) BLOCKERs — exactly at our internal bid/no-bid tolerance. We are bidding, but the four blockers in §4.1, §4.2, §4.3, and §4.4 are conditions of award. We request a 60-minute redline call between our Counsel and Sarah Chen / Marcus Webb before 2026-05-26.

7. Competitive Differentiation

Acme has named four other vendors. We respect every one of them. Our position relative to each:

| Competitor | Likely pitch | Their weakness on Acme's requirements | Our counter — evidence-based |
| --- | --- | --- | --- |
| Microsoft Fabric | "Free with E5" — sunk-cost framing of your existing Azure spend. | Real-time governance and per-table residency are 12–18 months behind. OneLake lock-in eliminates open-format portability. | TCO model includes the unbundled Professional Services cost for real-time governance — we will publish ours in writing. Precedent: Initech Sensors (2025-11) won against the same Fabric pitch. |
| Databricks | Pure Lakehouse, Delta Lake + Spark + MLflow, open-source heritage. | TCO opacity. Spark compute scales 4–6× on interactive BI workloads. Customer carries optimisation burden. | 3-year TCO comparison at Acme's actual workload profile. Multi-cloud optionality. Power BI DirectQuery maturity over Databricks SQL endpoint. Precedent: Globex Manufacturing (2025-09). |
| Snowflake | "Safe choice" — mature, easy SQL, broad ecosystem. | Native Iceberg support immature. Streaming requires Snowpipe plus external Kafka tooling. Dual-platform tax for IoT + analytics. | Lakehouse-native streaming + batch on a single engine. Open formats (Delta + Iceberg + Parquet) without external sidecars. Predictable, capped escalator pricing. |
| Regional vendor (unnamed) | Aggressive price; likely open-source stack (Trino + Iceberg) or European warehouse. | No enterprise SLA at 99.95%+. No Power BI DirectQuery adapter. Manual ETL bridges. | For 600-analyst Power BI estate plus a 18-month Teradata cutover, the consulting cost gap dwarfs the licence-fee savings. |

Three differentiation themes we ask Acme to weigh

1. Real-time + governance maturity.  Power BI DirectQuery adapter, 80K events/sec proven, per-table EU residency on customer-owned storage — all three in one stack.

2. TCO predictability and portability.  Open formats, customer-owned object storage, multi-cloud. Acme is never one re-platforming away from another vendor.

3. Power BI integration depth.  Dedicated DirectQuery adapter for your existing 600 analysts. Lowest-friction path off Teradata.

8. Customer References

All three references below are comparable on scale, Power BI deployment, and Azure footprint. We will arrange a structured reference call between Sarah Chen, Marcus Webb, and each reference customer's sponsor on request.

Reference 1 — Initech Sensors (closest comparable)

| Industry | Industrial / IoT — direct comparable to Acme |
| --- | --- |
| Annual contract value | $420,000 |
| Term | 2 years (2025–2027) |
| Competitors displaced | Microsoft Fabric |
| Won on | Real-time ingest performance and governance maturity. Microsoft Fabric was offering "free with E5" but could not match real-time SLA. |
| Power BI footprint | Yes — production deployment |
| Azure footprint | Yes |

Reference 2 — Globex Manufacturing

| Industry | Industrial / Manufacturing |
| --- | --- |
| Annual contract value | $580,000 |
| Term | 3 years (2025–2028) |
| Competitors displaced | Snowflake, Databricks |
| Won on | TCO and multi-cloud flexibility. Customer arrived favouring Snowflake; 3-year TCO comparison at actual workload profile (heavy unstructured) closed the case for BTS-Synthetic. |
| Power BI footprint | Yes |
| Azure footprint | Yes (primary), multi-cloud retained |

Reference 3 — Stark Industries

| Industry | Defence / Aerospace |
| --- | --- |
| Annual contract value | $1,100,000 |
| Term | 5 years (2026–2031) |
| Competitors displaced | Databricks, Snowflake, Microsoft Fabric |
| Won on | Sovereign deployment and IP licence-back model. Stark initially demanded full IP assignment of custom work (same as Acme §4.4); we offered perpetual royalty-free licence-back and Stark accepted. |
| Power BI footprint | Yes |
| Azure footprint | Yes |
| Relevance to Acme | Sets the contractual precedent for our position on §4.4 in this RFP. |

Capability Matrix attachment (per RFP §7): submitted separately under cover of this response.

9. Risk Register — Top 3

| # | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Source-system discovery overruns M0 | High | High | M0 is a fixed 4-week discovery sprint with explicit gating before M3. Migration schedule is not committed in writing until M0 sign-off by Acme CDO. 90-day buffer at M7 absorbs schedule slip. |
| R2 | Streaming latency requirement emerges below 250 ms after contract signature | Low | High | Clarification question lodged in §11. We will not contract to sub-100ms end-to-end without confirmed scope. If Acme requires sub-100ms for predictive maintenance alerting, we will scope a co-engineered solution as a change order rather than commit at signature. |
| R3 | Microsoft Fabric counter-bid undercuts on bundled E5 economics | Medium | Medium | Pre-emptive published TCO model including unbundled Professional Services for real-time governance and per-table residency. Reference: Initech Sensors won the same competitive scenario on TCO maturity, not on opening price. |

10. Vendor Stability

BTS-Synthetic operates a financially stable, profitable enterprise software business with multi-year visibility on revenue. Compliance posture: SOC 2 Type II, ISO 27001, HIPAA-eligible, GDPR-aligned (DPA available), FedRAMP Moderate (US Government tier). Audited financials and current attestation reports available under NDA on request to procurement@acme-synthetic.example.

11. Clarification Questions for Acme

To finalise our binding response, we request written answers to the following before contract signature. None of these block submission of this proposal:

Q1. Streaming latency SLO —  What is the maximum acceptable end-to-end streaming latency, particularly for the predictive maintenance alerting use case? Our standard is 250 ms – 1 s p99; sub-100ms is achievable only via co-engineering and should be scoped accordingly.

Q2. EU region selection —  Confirmation of Acme's EU region preference (e.g. North Europe, West Europe). We will validate residency coverage for the specific data model in our pre-signature solutioning sprint.

Q3. Source system documentation availability —  For schedule planning at M0, confirmation that Acme will provide source-system documentation and named technical owners for the 30+ batch sources within Weeks 1–2 of kickoff.

Q4. Pre-submission legal redline call —  Procurement (Sarah Chen) and CDO (Marcus Webb) to confirm availability before 2026-05-26 for a 60-minute redline call covering §4.1, §4.2, §4.3, §4.4.

Closing

We have written this response to score against the criteria Acme has set: functional fit first, then total cost of ownership, then commercial terms, then implementation, then stability. Where our position differs from your draft contract, we have said so plainly and proposed workable counter-positions backed by real customer precedent.

Direct any questions, redline requests, or scheduling for the legal review call to procurement@acme-synthetic.example or to your BTS-Synthetic account team.

— BTS-Synthetic Deal Desk

CONFIDENTIAL — BTS-Synthetic response to Acme Corp RFP dated 2026-05-12. Submitted 2026-05-26. Commercial terms subject to mutual contract execution.